## Cross-team contacts
Team (owner) | Card | Depends on team | Depends on card/artifact | Interface (format/protocol) | Timing (when needed) | Risk if late/missing | Notes
T1 Data | Design canonical schema | T2 Forecast, T3 Graph, T4 Context, T5 Anomaly | Consumer field lists (which columns each team needs) | Design doc + fixture JSON in repo (schema v0.1) | Week 1 — Contract Gate | All four research teams start late. Cascading impact. | Data owns canonical schema draft; other teams review and confirm required fields.
T1 Data | Publish fixture bundle | All teams (2, 3, 4, 5, 6, 7, 8) | Versioned Parquet/JSON fixtures in repo | Files at agreed path; teams pull as data source | Week 1 (initial), Week 2 (main dataset) | Any team unable to develop without live Kafka is blocked | Non-blocking rule: fixtures must work with no Kafka.
T1 Data | Publish canonical events | T7 Platform | Kafka producer conforming to Team 7's producer template | Kafka topic `sales.canonical.ready`, versioned schema | Week 3 — Foundation Gate | Downstream services can't consume real events | Team 7's service template + schema registry required first.
T1 Data | Synthetic scenario catalog | T5 Anomaly, T6 Explain, T8 Product | Documented scenarios: promotion failure, peer divergence, drift, weather contradiction | Deterministic replay stream + scenario docs | Week 3 (draft), Week 4 (main) | T5 can't evaluate detectors; T6/T8 can't build demo cases | T5 may inject anomalies locally as fallback but scenarios need to be shared.
T1 Data | Freeze canonical contract | All research teams | Written commitment: no breaking schema changes after this point | Schema version tag + release notes | Week 6 — Integration Gate | Late schema changes break downstream services in Weeks 7-9 | Backwards-compatible changes still allowed with version bump.
T2 Forecast | Consume canonical events (build) | T1 Data | Fixture bundle (Week 1); Kafka `sales.canonical.ready` (Week 3+) | Parquet/JSON initially; Kafka topic later | Week 1 (fixture), Week 3 (Kafka) | Can build feature pipeline on fixtures; Kafka only blocks final integration | Simple baseline runs from fixture bundle alone.
T2 Forecast | Publish forecast.completed | T7 Platform | Kafka producer via Team 7 service template | Kafka topic `forecast.completed` with agreed schema | Week 3 — Foundation Gate | T6 Explain and T8 UI can't use real forecast (must use mocks) | Baseline forecast is the permanent demo fallback.
T2 Forecast | Publish forecast.completed schema | T6 Explain, T8 Product | Schema doc + mock payload example | JSON schema in repo, mock producer | Week 1 — Contract Gate | T6 and T8 use mocks; low risk if schema stays stable | Every field they'll rely on must be in the mock from Week 1.
T3 Graph | Consume canonical events (build) | T1 Data | Fixture bundle (Week 1); Kafka `sales.canonical.ready` (Week 3+) | Parquet/JSON initially; Kafka topic later | Week 1 (fixture), Week 3 (Kafka) | Baseline peer similarity runs from fixture alone | Store metadata (location, size, region) especially needed.
T3 Graph | Publish peer.completed | T7 Platform | Kafka producer via Team 7 service template | Kafka topic `peer.completed` with agreed schema | Week 3 — Foundation Gate | T6 Explain and T8 UI must use mocks | Simple similarity baseline is permanent demo fallback.
T3 Graph | Neo4j / graph DB access | T7 Platform | Neo4j instance in shared integration environment | Neo4j URL + credentials, provisioned via Compose | Week 3 (optional), Week 5 (needed for graph queries) | GNN research runs standalone; only service integration needs Neo4j | Baseline peer method doesn't need graph DB.
T3 Graph | Publish peer.completed schema | T6 Explain, T8 Product | Schema doc + mock payload example | JSON schema in repo, mock producer | Week 1 — Contract Gate | T6 and T8 use mocks; low risk if schema stays stable | Peer set + peer-deviation metric are the key fields.
T4 Context | Consume canonical events (build) | T1 Data | Fixture bundle (Week 1); Kafka `sales.canonical.ready` (Week 3+) | Parquet/JSON initially; Kafka topic later | Week 1 (fixture), Week 3 (Kafka) | Baseline with/without-context runs from fixture alone | Store IDs and geography (for weather joins) especially needed.
T4 Context | Publish context.completed | T7 Platform | Kafka producer via Team 7 service template | Kafka topic `context.completed` with agreed schema | Week 3 — Foundation Gate | T6 Explain and T8 UI must use mocks | Simple with-context baseline is fallback.
T4 Context | External weather API | External (Open-Meteo) | Historical + forecast weather by lat/lon | HTTP API, cache locally | Week 2 onward | Weather features unavailable; degrade to holiday/promo only | Cache aggressively; demo must not require live external call.
T4 Context | Publish context.completed schema | T6 Explain, T8 Product | Schema doc + mock payload example | JSON schema in repo, mock producer | Week 1 — Contract Gate | T6 and T8 use mocks; low risk if schema stays stable | Contradiction score + explanation fields are the key items.
T5 Anomaly | Consume canonical events (build) | T1 Data | Fixture bundle (Week 1); Kafka `sales.canonical.ready` (Week 3+) | Parquet/JSON initially; Kafka topic later | Week 1 (fixture), Week 3 (Kafka) | Independent training on fixture; only integration needs Kafka | Explicitly: does NOT wait for forecast/graph/context signals.
T5 Anomaly | Consume synthetic scenarios | T1 Data | Injected anomaly scenarios (spikes, drops, drift, missing uplift) | Deterministic replay stream + scenario labels | Week 2 (evaluation harness), Week 4 (drift ensemble) | Can't measure Precision/Recall without labeled anomalies | T5 can inject locally as fallback but shared scenarios are more valuable.
T5 Anomaly | Publish anomaly.detected | T7 Platform | Kafka producer via Team 7 service template | Kafka topic `anomaly.detected` with agreed schema | Week 3 — Foundation Gate | T6 and T8 must use mocks; demo of end-to-end flow blocked | Residual baseline is permanent fallback.
T5 Anomaly | Publish drift.detected | T7 Platform, T8 Product | Kafka producer via Team 7 service template | Kafka topic `drift.detected` with agreed schema | Week 3 (v1), Week 6 (final) | T8 dashboard can't show persistent-vs-temporary distinction | CUSUM baseline is permanent fallback.
T5 Anomaly | Publish anomaly/drift schemas | T6 Explain, T8 Product | Schema docs + mock payloads | JSON schemas in repo, mock producers | Week 1 — Contract Gate | T6 uses mocks for explanation development | Anomaly type, score, timestamp, and evidence fields are critical.
T6 Explain | Consume anomaly.detected | T5 Anomaly | Kafka topic `anomaly.detected` (or mock) | Kafka consumer via Team 7 service template | Week 1 (mock), Week 3 (real) | Uses T5's mock payloads until real service ready | Primary trigger for T6 to run.
T6 Explain | Consume forecast.completed (evidence) | T2 Forecast | Kafka topic `forecast.completed` (optional evidence) | Kafka consumer | Week 3 (mock), Week 4+ (real) | Explanation degrades gracefully — missing forecast → less evidence | T6 designs explanation payload with optional/versioned fields.
T6 Explain | Consume peer.completed (evidence) | T3 Graph | Kafka topic `peer.completed` (optional evidence) | Kafka consumer | Week 3 (mock), Week 4+ (real) | Explanation degrades gracefully without peer signal | Peer deviation is a strong explanation signal when present.
T6 Explain | Consume context.completed (evidence) | T4 Context | Kafka topic `context.completed` (optional evidence) | Kafka consumer | Week 3 (mock), Week 4+ (real) | Explanation degrades gracefully without context signal | Context contradiction is a strong explanation signal.
T6 Explain | Consume drift.detected | T5 Anomaly | Kafka topic `drift.detected` (optional evidence) | Kafka consumer | Week 3 (mock), Week 4+ (real) | Drift adds persistent-vs-temporary distinction to explanation | Same producer as anomaly.detected; low integration cost.
T6 Explain | Business impact inputs (price/margin/inventory) | T1 Data | Reference tables in canonical schema (price, margin proxies) | Included in canonical events or fetched from shared store | Week 2 (fixture), Week 4 (impact formula) | Impact formula must document assumptions if fields unavailable | T6 must be explicit about proxy assumptions.
T6 Explain | Publish explanation.completed and impact.completed | T7 Platform, T8 Product | Kafka producers via Team 7 service template | Kafka topics with agreed schemas | Week 3 — Foundation Gate | T8 dashboard can't render explanation/priority | Rule-based baseline is permanent fallback.
T7 Platform | Provide Kafka + Compose environment | All research + product teams | Runnable Kafka/Redpanda + Postgres in Docker Compose | docker-compose up, documented ports/credentials | Week 1 — Contract Gate | Every team's integration path blocked | Fixture-first rule lets research proceed even if this slips.
T7 Platform | Provide service template + mock producer/consumer | T2, T3, T4, T5, T6 | Reusable FastAPI service template with Kafka producer/consumer + tests | Repo module + docs | Week 1 — Contract Gate | Each research team reinvents integration boilerplate | Template should be copy-pasteable, not imported.
T7 Platform | Collect schemas from producing teams | T1, T2, T3, T4, T5, T6 | Agreed JSON schema per Kafka topic (owned by producer) | Contract test suite verifies each schema | Week 1 (draft), Week 2 (contract tests) | Schema drift breaks downstream services silently | Producer owns schema; Platform provides validation harness.
T7 Platform | Provide backend query APIs | T8 Product | REST API gateway with query endpoints for anomalies/services | OpenAPI spec + running service | Week 3 (initial), Week 5 (full) | T8 falls back to direct Kafka consumption or mocks | T8 can test with curl/mocks until real API ready.
T7 Platform | OpenTelemetry / metrics hooks | T8 Product | Prometheus exporters + OTel traces in every service | Prometheus endpoints, standard metric names | Week 5 — Grafana panels connected | T8's Grafana view shows mock metrics only | Coordinate metric names/labels early; renames break dashboards.
T7 Platform | Retry/idempotency/DLQ strategy | All Kafka-producing teams | Documented pattern; DLQ topic per producer | Pattern doc + optional code helper | Week 4 — real event flow | Poison messages take down consumers | Every producer must publish idempotently or teams see duplicates.
T7 Platform | Integration Gate ownership | All teams | Complete event flow from T1 through T8 works end-to-end | Live demo of full pipeline | Week 6 — Integration Gate | Cohort-wide gate failure; recovery affects all teams | Platform is primary owner; every producing team must be integrated.
T8 Product | Consume backend query APIs | T7 Platform | REST API from Team 7's backend gateway | OpenAPI-defined endpoints | Week 1 (mock), Week 3 (real) | UI falls back to mock JSON responses | Mock responses in fixtures/ so UI works without backend.
T8 Product | Consume all model output schemas (for rendering) | T2, T3, T4, T5, T6 | Producers' JSON schemas for UI component contracts | Schema docs + mock payloads | Week 1 — Contract Gate | UI components hardcode wrong field names | T8 should own a canonical 'display schema' referencing each producer's fields.
T8 Product | Consume Prometheus metrics | T7 Platform, all service teams | Metrics endpoints from each service | Prometheus scrape config; Grafana dashboards | Week 5 — Grafana panels live | Grafana shows only mock data | Standard metric names required early.
T8 Product | Optional Slack alert integration | T7 Platform (transport), T6 Explain (severity) | Alert transport + priority-scored anomaly events | HTTP webhook + Kafka `alert.requested` | Week 7 (stretch) | Feature-flagged; core demo works without | P2 stretch — only after core demo is stable.
T8 Product | Demo orchestration | All teams | Seeded scenario runs end-to-end through the system | Coordinated with T1 (data), T7 (infra) | Week 8 — Demo-Readiness Gate | Demo fails or is not reproducible | T8 owns demo flow but every team's service must cooperate.

## Topic map
Kafka topic | Producer team | Consumer teams | Notes
sales.canonical.ready | T1 Data | T2 Forecast, T3 Graph, T4 Context, T5 Anomaly | The one topic that fans out to all research teams.
forecast.completed | T2 Forecast | T6 Explain, T8 UI | Optional evidence for T6; display data for T8.
peer.completed | T3 Graph | T6 Explain, T8 UI | Optional evidence for T6; display data for T8.
context.completed | T4 Context | T6 Explain, T8 UI | Optional evidence for T6; display data for T8.
anomaly.detected | T5 Anomaly | T5 (self, for drift), T6 Explain, T8 UI | Primary trigger for T6's explanation pipeline.
drift.detected | T5 Anomaly | T8 UI (optional retraining trigger) | Persistent-vs-temporary distinction for dashboard.
explanation.completed | T6 Explain | T7 Backend, T8 UI | The 'why' payload for the manager UI.
impact.completed | T6 Explain | T7 Backend, T8 UI | The business priority score for ranking.
alert.requested | T6 or T8 | T8 UI + optional Slack | Optional; feature-flagged. P2 stretch.